# Azure Migration HLD — Fictional Northstar Research Group

Project Aurora | High-Level Design

FICTIONAL DEMONSTRATION — NOT A CUSTOMER DOCUMENT

This source DOCX is the authoritative template. DocXUnravel populates only contract-bound elements.

# Document Control

| Field | Value |
| --- | --- |
| Customer | Fictional Northstar Research Group |
| Project | Fictional Project Aurora Azure Migration |
| Sponsor | Fictional Morgan Reed |
| Document owner | Fictional Avery Patel |
| Target start | 2027-01-11 |
| Target completion | 2027-07-30 |

# Executive Summary

Fictional migration of three demonstration applications and their supporting data services to a governed Azure landing zone.

# Current-State Assessment

The observations below are populated from validated migration-discovery records.

| Category | Observation | Impact |
| --- | --- | --- |
| Fictional resilience observation | Fictional recovery procedures rely on manual virtual-machine restoration. | Fictional recovery objectives may not be met during a regional incident. |
| Fictional operations observation | Fictional application telemetry is retained in separate local tools. | Fictional incident diagnosis requires cross-team log collection. |
| Fictional security observation | Fictional privileged service accounts use long-lived credentials. | Fictional credential exposure would increase lateral-movement risk. |

# Application Inventory

| ID | Application | Owner | Criticality | Current hosting | Data class | Disposition |
| --- | --- | --- | --- | --- | --- | --- |
| FICTIONAL-APP-001 | Fictional Atlas Portal | Fictional Research Operations | high | Fictional IIS virtual machines | confidential | replatform |
| FICTIONAL-APP-002 | Fictional Beacon Scheduler | Fictional Laboratory Services | critical | Fictional Windows service cluster | restricted | refactor |
| FICTIONAL-APP-003 | Fictional Cedar Archive | Fictional Records Team | medium | Fictional file and SQL servers | internal | rehost |

# Target Architecture

The existing illustration is a read-only package asset retained during population.

Figure 1 — Fictional Azure target architecture (pre-existing template asset)

| Workload | Azure service | Region | Rationale |
| --- | --- | --- | --- |
| Fictional Atlas Portal | Azure App Service | UK South | Fictional managed web hosting reduces operating-system management. |
| Fictional Beacon Scheduler | Azure Kubernetes Service | UK South | Fictional container orchestration supports isolated scheduling workers. |
| Fictional relational data tier | Azure SQL Managed Instance | UK South | Fictional compatibility requirements favour managed SQL Server semantics. |
| Fictional Cedar Archive | Azure Files | UK West | Fictional SMB compatibility supports phased application migration. |

# Migration Strategy

Migration waves are sequenced by dependency, risk and operational readiness.

| Wave | Name | Applications | Start | End | Exit criteria |
| --- | --- | --- | --- | --- | --- |
| 1 | Fictional foundation and Cedar pilot | FICTIONAL-APP-003 | 2027-01-11 | 2027-03-05 | Fictional landing-zone controls pass and Cedar backup restoration is demonstrated. |
| 2 | Fictional Atlas replatform | FICTIONAL-APP-001 | 2027-03-08 | 2027-05-14 | Fictional Atlas performance and recovery tests meet agreed targets. |
| 3 | Fictional Beacon refactor | FICTIONAL-APP-002 | 2027-05-17 | 2027-07-30 | Fictional end-to-end scheduling and security accreditation are complete. |

# Security Considerations

## Security requirements

| ID | Requirement | Priority |
| --- | --- | --- |
| FICTIONAL-SEC-001 | Fictional workloads must use managed identities where supported. | must |
| FICTIONAL-SEC-002 | Fictional confidential and restricted data must be encrypted with customer-managed keys. | must |

## Networking requirements

| ID | Requirement | Priority |
| --- | --- | --- |
| FICTIONAL-NET-001 | Fictional production ingress must traverse Azure Application Gateway with WAF enabled. | must |
| FICTIONAL-NET-002 | Fictional platform services should use private endpoints and central DNS resolution. | should |

# Risks and Assumptions

## Risks

| ID | Description | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| FICTIONAL-RISK-001 | Fictional laboratory integrations may use undocumented source addresses. | medium | high | Fictional packet capture and owner validation before wave planning. |
| FICTIONAL-RISK-002 | Fictional SQL compatibility testing may identify unsupported features. | medium | medium | Fictional compatibility assessment and rollback rehearsal. |

## Assumptions

| ID | Description | Validation owner |
| --- | --- | --- |
| FICTIONAL-ASM-001 | Fictional ExpressRoute connectivity will be available before the first migration wave. | Fictional Network Lead |
| FICTIONAL-ASM-002 | Fictional application owners will provide representative performance tests. | Fictional Programme Lead |

# Appendix

## Outstanding design decisions

| ID | Decision | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| FICTIONAL-DD-001 | Fictional selection of active-passive or active-active regional recovery for Beacon. | Fictional Solution Design Authority | 2027-02-12 | open |
| FICTIONAL-DD-002 | Fictional retention period for migrated Cedar archive data. | Fictional Records Owner | 2027-02-19 | in_review |

## Source infrastructure inventory

| ID | Name | Category | Location | Quantity | OS | Specification |
| --- | --- | --- | --- | --- | --- | --- |
| FICTIONAL-INF-001 | Fictional VMware application cluster | compute | Fictional London data centre | 12 | Fictional mix of Windows Server 2019 and Ubuntu 22.04 | Fictional 8 vCPU and 32 GiB RAM average virtual machine |
| FICTIONAL-INF-002 | Fictional SQL Server availability group | database | Fictional London data centre | 2 | Fictional Windows Server 2019 | Fictional SQL Server 2019 Enterprise with 4 TiB allocated storage |
| FICTIONAL-INF-003 | Fictional research file estate | storage | Fictional Manchester data centre | 1 | Fictional storage appliance OS | Fictional 18 TiB used capacity with 12 percent annual growth |

## Application dependencies

| Source | Target | Type | Notes |
| --- | --- | --- | --- |
| FICTIONAL-APP-001 | FICTIONAL-APP-002 | synchronous | Fictional HTTPS scheduling request dependency. |
| FICTIONAL-APP-002 | FICTIONAL-APP-003 | file | Fictional nightly result archive transfer. |